## Sayfa1
BARFAS | [8 empty] | NİSAN 2026
Burak YALIM
| Work Start Date | 2026-04-01 | [6 empty] | Week-1 | [6 empty] | Week-2 | [6 empty] | Week-3 | [6 empty] | Week-4 | [6 empty] | Week-5
Project Lead
[11 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29
| Service Type - Project Name |  | PREDECESSOR | START | END | % DONE | HOURS | MINUTES | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
# | Hardware Development |  |  |  | - |  |  | -
1
# | Software Development |  |  |  | - |  |  | -
1 | Smart Access Controller(Duvar) |  |  | 2026-04-01 |  |  | 4 | 0 | bar: 1899-12-31
2 | Smart Access Controller(Duvar) |  |  | 2026-04-04 |  |  | 8 | 0 | bar: 1900-01-03
3 | Smart Access Controller(Duvar) |  |  | 2026-04-06 |  |  | 3 | 40 | bar: 1900-01-05
4 | Smart Access Controller(Duvar) |  |  | 2026-04-11 |  |  | 8 | 20 | bar: 1900-01-10
5 | Smart Access Controller(Duvar) |  |  | 2026-04-14 |  |  | 2 | 0 | bar: 1900-01-13
6 | Gateway (Bluetooth) |  |  | 2026-04-16 |  |  | 4 | 0 | bar: 1900-01-15
7 | Gateway (Bluetooth) |  |  | 2026-04-19 |  |  | 8 | 20 | bar: 1900-01-18
8 | Smart Access Controller(Duvar) |  |  | 2026-04-22 |  |  | 3 | 0 | bar: 1900-01-21
9 | Smart Access Controller(Duvar) |  |  | 2026-04-25 |  |  | 5 | 30 | bar: 1900-01-24
10 | Smart Access Controller(Duvar) |  |  | 2026-04-28 |  |  | 2 | 0 | bar: 1900-01-27
11 | Smart Access Controller(Duvar) |  |  | 2026-04-29 |  |  | 3 | 0 | bar: 1900-01-28
12 | Smart Access Controller(Duvar) |  |  | 2026-04-30 |  |  | 3 | 30 | bar: 1900-01-29
| Total Hours | [5 empty] | 58 | 0
Formulas:
MINUTES = IF(OR([END]=0,[START]=0)," - ",NETWORKDAYS([START],[END]))
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.